## Лист1
№ | Task | Duration | Dependencies
Requirements and Architecture specification
1 | SRS development | 14
2 | Architecture description | 5
DB development
3 | Domain analysis | 2 | 1,2(M1)
4 | ER-diagram development | 2 | 1,2(M1)
5 | DB development (MS SQL) | 5 | 3,4(M2)
6 | Documentation development | 3 | 5(M3)
Computing module development
7 | Reqs identification | 2 | 6(M4)
8 | Coding | 7 | 7(M5)
9 | Unit testing | 4 | 8(M6)
10 | Documentation development | 2 | 8(M6)
Exporting module development
11 | Reqs identification | 2 | 6(M4)
12 | Coding | 7 | 11(M7)
13 | Unit testing | 4 | 12(M8)
14 | Documentation development | 2 | 12(M8)
Client application development
15 | Reqs identification | 1 | 6(M4)
16 | Coding | 10 | 15(M9)
17 | Unit testing | 4 | 16(M10)
18 | Documentation development | 2 | 16(M10)
Deployment
19 | Module integration testing | 15 | 9,13,17(M11)
20 | Testing report preparation | 3 | 10,14,18,19(M12)
21 | Introduction | 4 | 20(M13)